## Sheet1
Revised | TAG NUMBER | Status | MOC | Line Number | SIZE (inch) | Service Description | Bulk ID Long | General Material Description | Quantity | Product Code | Remarks | Project Number | Weight
Batch 25/27 | 110-VABL-1025 | CONFIRMED |  | 110-LPGN-2217 | 0.75 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02-A PAINT A | BL02-A-0.75-A | CARBON STEEL | 1 | BLK.VLV.BAL.CST | Yard Scope | SO17033 | 12
Batch 25 | 110-VABL-1026 | CONFIRMED |  | 110-LPGN-2217 | 2 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02-A PAINT A | BL02-A-2-A | CARBON STEEL | 1 | BLK.VLV.BAL.CST | Yard Scope | SO17033 | 22
Batch 25 | 110-VABL-5009 | OUT OF SCOPE | MoC-PF-031 | 110-LPGN-0052 | 2 | VALVE BALL FLOATING FB CL 150 FF BRONZE ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-2-A | COPPER | 1 | BLK.VLV.BAL.BRO |  | SO17033 | 21
Batch 25 | 112-VABL-7100 | OUT OF SCOPE | MoC-VE-025 | 118-LPAI-0090 | 0.5 | VALVE BALL TRUNNION FB 3000 PSI COMPRESSION SS SWAGELOK LEVER BL55N-P PAINT A | BL55N-P-0.5-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 7
Batch 25 | 112-VABL-7101 | OUT OF SCOPE | MoC-VE-025 | 118-LPAI-0091 | 0.5 | VALVE BALL TRUNNION FB 3000 PSI COMPRESSION SS SWAGELOK LEVER BL55N-P PAINT A | BL55N-P-0.5-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 7
Batch 25 | 112-VABL-7102 | OUT OF SCOPE | MoC-VE-025 | 118-LPAI-0092 | 0.5 | VALVE BALL TRUNNION FB 3000 PSI COMPRESSION SS SWAGELOK LEVER BL55N-P PAINT A | BL55N-P-0.5-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 7
Batch 25 | 112-VABL-7103 | OUT OF SCOPE | MoC-VE-025 | 118-LPAI-0093 | 0.5 | VALVE BALL TRUNNION FB 3000 PSI COMPRESSION SS SWAGELOK LEVER BL55N-P PAINT A | BL55N-P-0.5-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 7
Batch 25/27 | 113-VABL-1015 | CONFIRMED |  | 113-LPDH-2725 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 21
Batch 25 | 113-VABL-1017 | CONFIRMED |  | 113-LPDH-2721 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 21
Batch 25 | 113-VABL-1018 | CONFIRMED |  | 113-LPDH-2725 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 21
Batch 25 | 113-VABL-1019 | CONFIRMED |  | 113-LPDH-2725 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 21
Batch 25/27 | 113-VABL-1021 | CONFIRMED |  | 113-LPDH-2725 | 0.75 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-0.75-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 12
Batch 25/27 | 113-VABL-1022 | CONFIRMED |  | 113-LPDH-2725 | 0.75 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-0.75-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 12
Batch 19 | 113-VACH-0999 | OUT OF SCOPE |  | 1-DH113999 | 1 | VALVE CHECK STOPCHECK RF CL 150 CS ASME B16.10 HANDWHEEL CH07N-A PAINT - A | CH07N-A-1-A | CARBON STEEL | 0 | BLK.VLV.CHK.CST | MPF | SO17033 | 4
Batch 22 | 116-VABL-0623 | OUT OF SCOPE |  |  | 1.5 | VALVE BALL FLOATING FB CL 150 FF AL-BRONZE ASME B16.10 LG LEVER BL42-A PAINT A | BL42-A-1.5-A | Ni-Aluminum Bronze | 0 | BLK.VLV.BAL.ALB | MPF | SO17033 | 22
Batch 22 | 116-VABL-0624 | OUT OF SCOPE |  |  | 1.5 | VALVE BALL FLOATING FB CL 150 FF AL-BRONZE ASME B16.10 LG LEVER BL42-A PAINT A | BL42-A-1.5-A | Ni-Aluminum Bronze | 0 | BLK.VLV.BAL.ALB | MPF | SO17033 | 22
Batch 25 | 118-VABL-1051 | CONFIRMED |  | 118-LPAU-2071 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 21
Batch 25/27 | 118-VABL-1052 | CONFIRMED |  | 118-LPAU-2071 | 0.75 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-0.75-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard Scope | SO17033 | 12
Batch 25 | 118-VABL-1462 | CONFIRMED | MoC-TS-300 | 118-LPAI-2316 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard scope | SO17033 | 21
Batch 25 | 118-VABL-1463 | CONFIRMED | MoC-TS-300 | 118-LPAI-2316 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard scope | SO17033 | 21
Batch 25 | 118-VABL-1464 | CONFIRMED | MoC-TS-300 | 118-LPAI-2316 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard scope | SO17033 | 21
Batch 25 | 118-VABL-1465 | CONFIRMED | MoC-TS-300 | 118-LPAI-2316 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST | Yard scope | SO17033 | 21
Batch 24/25/26 | 118-VABL-5006 | OUT OF SCOPE | No MoC yet | 118-LPAI-2316 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | Line number updated. PMC updated, was AE7N | SO17033 | 21
Batch 24/25 | 118-VABL-5105 | OUT OF SCOPE | MoC-VE-048 | 118-LPAI-0035 | 2 | VALVE BALL FLOATING FB CL 150 FF BRONZE ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-2-A | COPPER | 1 | BLK.VLV.BAL.BRO | Instrumentation Scope | SO17033 | 21
Batch 25 | 118-VABL-5111 | OUT OF SCOPE | MoC-VE-048 | 118-LPAI-0019 | 2 | VALVE BALL FLOATING FB CL 150 RF SS ASME B16.10 LG LEVER BL52-A PAINT A | BL52-A-2-A | STAINLESS STEEL | 1 | BLK.VLV.BAL.SST |  | SO17033 | 21
Batch 25 | 118-VABL-5112 | OUT OF SCOPE | MoC-VE-048 | 118-LPAI-0084 | 2 | VALVE BALL FLOATING FB CL 150 FF BRONZE ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-2-A | COPPER | 1 | BLK.VLV.BAL.BRO | Instrumentation Scope | SO17033 | 21
Batch 25 | 118-VABL-5117 | OUT OF SCOPE | MoC-PF-031 | 118-LPAU-0055 | 1.5 | VALVE BALL FLOATING FB CL 150 FF BRONZE ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-1.5-A | COPPER | 1 | BLK.VLV.BAL.BRO | Hold for correct tag number | SO17033 | 22
Batch 25 | 118-VABL-5118 | OUT OF SCOPE | MoC-PF-031 | 118-LPAU-0056 | 1.5 | VALVE BALL FLOATING FB CL 150 FF BRONZE ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-1.5-A | COPPER | 1 | BLK.VLV.BAL.BRO | Hold for correct tag number | SO17033 | 22
Batch 25/27 | 121-VABL-1003 | CONFIRMED |  | 121-LPWZ-2021 | 0.75 | VALVE BALL FLOATING FB CL 150 FF COPPER ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-0.75-A | COPPER | 1 | BLK.VLV.BAL.BRO | Yard Scope | SO17033 | 12
Batch 25 | 121-VABL-1004 | CONFIRMED |  | 121-LPWZ-2021 | 2 | VALVE BALL FLOATING FB CL 150 FF COPPER ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-2-A | COPPER | 1 | BLK.VLV.BAL.BRO | Yard Scope | SO17033 | 21
Batch 25 | 121-VABL-1139 | CONFIRMED |  | 121-LPWZ-2071 | 2 | VALVE BALL FLOATING FB CL 150 FF COPPER ASME B16.10 LG LEVER BL33-A PAINT A | BL33-A-2-A | COPPER | 1 | BLK.VLV.BAL.BRO | Yard Scope | SO17033 | 21
Batch 27 | 122-VADI-7000 | OUT OF SCOPE |  | 122-LPWS-0001 | 2 | VALVE DIAPHRAGM RF CL 150 DUCTILE IRON BS 13397 LEVER DI01-A PAINT A | DI01-A-2-A | DUCTILE IRON | 0 | BLK.VLV.DIA.CST |  | SO17033 | 9.3
Batch 27 | 122-VADI-7001 | OUT OF SCOPE |  | 122-LPWS-0005 | 1 | VALVE DIAPHRAGM RF CL 150 DUCTILE IRON BS 13397 LEVER DI01-A PAINT A | DI01-A-1-A | DUCTILE IRON | 0 | BLK.VLV.DIA.CST |  | SO17033 | 5
Batch 27 | 122-VADI-7100 | OUT OF SCOPE |  | 122-LPWS-0020 | 0.5 | VALVE DIAPHRAGM RF CL 150 DUCTILE IRON BS 13397 LEVER DI01-A PAINT A | DI01-A-0.5-A | DUCTILE IRON | 0 | BLK.VLV.DIA.CST |  | SO17033 | 4
Batch 27 | 127-VABF-0625 | OUT OF SCOPE | MoC-VE-020 | 127-LPGI-0004 | 20 | VALVE BUTTERFLY LINED LUGGED RF CL 150 NODULAR CAST IRON API 609 A GEARBOX BF04-A PAINT A | BF04-A-20-A | Nodular CI | 0 | BLK.VLV.BFO. | MPF1 valve, relocated from line 20-FG127624-AQ5N | SO17033
Batch 27 | 127-VABF-5002 | OUT OF SCOPE |  | GI127628 | 10 | VALVE BUTTERFLY LINED LUGGED RF CL 150 NODULAR CAST IRON API 609 A GEARBOX BF04-A PAINT A | BF04-A-10-A | Nodular CI | 0 | BLK.VLV.BFO. | Vessel, Hull, Main Deck | SO17033 | 42.7
Batch 27 | 127-VABL-0717 | OUT OF SCOPE | MoC-VE-054 | 127-LPFG-0036 | 6 | VALVE BUTTERFLY LINED LUGGED RF CL 150 NODULAR CAST IRON API 609 A LEVER BF04-A PAINT A | BF04-A-6-A | Nodular CI | 0 | BLK.VLV.BFO. | use MPF valve | SO17033 | 11.4
Batch 27 | 127-VABL-0727 | OUT OF SCOPE | MoC-VE-054 | 127-LPFG-0036 | 0.75 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02N-A PAINT A | BL02N-A-0.75-A | CARBON STEEL | 0 | BLK.VLV.BAL.CST | use MPF valve | SO17033 | 12
Batch 27 | 127-VABL-0728 | OUT OF SCOPE | MoC-VE-020 | 127-LPGI-0004 | 0.75 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02N-A PAINT A | BL02N-A-0.75-A | CARBON STEEL | 0 | BLK.VLV.BAL.CST | MPF1 valve, relocated from line 20-FG127624-AQ5N | SO17033 | 12
Batch 20/21/22/27 | 128-VAGL-1133 | OUT OF SCOPE |  | 128-LTCM-2202 | 0.75 | VALVE GLOBE NEEDLE -TYPE COMPRESSION 3000 PSI SS SWAGELOK T-BAR HANDLE GL54N-P PAINT A | GL54N-P-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.GLB.SST | Bulk ID corrected to GL54N-P, to be procured by YARD | SO17033 | 4
Batch 20/21/22/27 | 128-VAGL-1134 | OUT OF SCOPE |  | 128-LTCM-2201 | 0.75 | VALVE GLOBE NEEDLE -TYPE COMPRESSION 3000 PSI SS SWAGELOK T-BAR HANDLE GL54N-P PAINT A | GL54N-P-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.GLB.SST | Bulk ID corrected to GL54N-P, to be procured by YARD | SO17033 | 4
Batch 21/22/27 | 128-VAGL-2007 | OUT OF SCOPE | MoC-TS-015 | 128-LTCL-2920 | 0.75 | VALVE GLOBE NEEDLE -TYPE COMPRESSION 3000 PSI SS SWAGELOK T-BAR HANDLE GL54N-P PAINT A | GL54N-P-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.GLB.SST | Bulk ID corrected to GL54N-P, to be procured by YARD | SO17033 | 4
Batch 27 | 331-VABF-0523 | OUT OF SCOPE | MoC-TS-177 | 331-LPWF-0045 | 3 | VALVE BUTTERFLY DOUBLE OFFSET LUGGED FF CL 150 AL-BRONZE API 609 B LEVER BF41-A PAINT A | BF41-A-3-A | ALUMINUM BRONZE | 0 | BLK.VLV.BFO.ALB | Demolition scope, to be re-used | SO17033 | 8.2
Batch 27 | 331-VABF-0524 | OUT OF SCOPE | MoC-TS-177 | 331-LPWF-0043 | 3 | VALVE BUTTERFLY DOUBLE OFFSET LUGGED FF CL 150 AL-BRONZE API 609 B LEVER BF41-A PAINT A | BF41-A-3-A | ALUMINUM BRONZE | 0 | BLK.VLV.BFO.ALB |  | SO17033 | 8.2
Batch 27 | 331-VABF-0679 | OUT OF SCOPE | MoC-TS-177 | 331-LPWF-0044 | 3 | VALVE BUTTERFLY DOUBLE OFFSET LUGGED FF CL 150 AL-BRONZE API 609 B LEVER BF41-A PAINT A | BF41-A-3-A | ALUMINUM BRONZE | 0 | BLK.VLV.BFO.ALB |  | SO17033 | 8.2
Batch 27 | 331-VACH-0559 | OUT OF SCOPE | MoC-TS-177 | 331-LPWF-0044 | 2 | VALVE CHECK SWING FF CL 150 AL-BRONZE API 6D CH41-A PAINT A | CH41-A-2-A | Ni-Aluminum Bronze | 0 | BLK.VLV.CHK.ALB |  | SO17033 | 15
Batch 27 | 331-VACH-0560 | OUT OF SCOPE | MoC-TS-177 | 331-LPWF-0045 | 2 | VALVE CHECK SWING FF CL 150 AL-BRONZE API 6D CH41-A PAINT A | CH41-A-2-A | Ni-Aluminum Bronze | 0 | BLK.VLV.CHK.ALB | Demolition scope, to be re-used | SO17033 | 15
Batch 27 | 331-VACH-0581 | OUT OF SCOPE | MoC-TS-333 | 331-LPWF-0043 | 2 | VALVE CHECK SWING FF CL 150 AL-BRONZE API 6D CH41-A PAINT A | CH41-A-2-A | Ni-Aluminum Bronze | 0 | BLK.VLV.CHK.ALB | Was 331-VACH-0505 | SO17033 | 15
Batch 20/21 | 771-VABL-4410 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2116 | 0.5 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02N-A PAINT B | BL02N-A-0.5-B | CARBON STEEL | 0 | BLK.VLV.BAL.CST | TS Mechanical Package | SO17033 | 10
Batch 20/21 | 771-VABL-4411 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2116 | 0.5 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02N-A PAINT B | BL02N-A-0.5-B | CARBON STEEL | 0 | BLK.VLV.BAL.CST | TS Mechanical Package | SO17033 | 10
Batch 20/21 | 771-VABL-4430 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2116 | 0.5 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02N-A PAINT B | BL02N-A-0.5-B | CARBON STEEL | 0 | BLK.VLV.BAL.CST | TS Mechanical Package | SO17033 | 10
Batch 20/21 | 771-VABL-4431 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2116 | 0.5 | VALVE BALL FLOATING FB CL 150 RF CS ASME B16.10 LG LEVER BL02N-A PAINT B | BL02N-A-0.5-B | CARBON STEEL | 0 | BLK.VLV.BAL.CST | TS Mechanical Package | SO17033 | 10
Batch 20/21 | 771-VADB-4400 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2101 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RF x NPTF CL 600 DSS MANU STD LEVER DB05N-D PAINT B | DB05N-D-0.5-B | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 4.7
Batch 20/21 | 771-VADB-4401 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2101 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RF x NPTF CL 600 DSS MANU STD LEVER DB05N-D PAINT B | DB05N-D-0.5-B | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 4.7
Batch 20/21 | 771-VADB-4402 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2101 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RF x NPTF CL 600 DSS MANU STD LEVER DB05N-D PAINT B | DB05N-D-0.5-B | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 4.7
Batch 20/21 | 771-VADB-4403 | OUT OF SCOPE | MoC-TS-088 | 771-LPPG-2101 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RF x NPTF CL 600 DSS MANU STD LEVER DB05N-D PAINT B | DB05N-D-0.5-B | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 4.7
Batch 20/21 | 771-VAMO-4416 | OUT OF SCOPE |  | 771-LPPG-2204 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 600 SS MANU STD T-BAR HANDLE MO51N-D PAINT A | MO51N-D-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 1.8
Batch 20/21 | 771-VAMO-4417 | OUT OF SCOPE |  | 771-LPPG-2204 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 600 SS MANU STD T-BAR HANDLE MO51N-D PAINT A | MO51N-D-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 1.8
Batch 20/21 | 771-VAMO-4418 | OUT OF SCOPE |  | 771-LPPG-2214 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 600 SS MANU STD T-BAR HANDLE MO51N-D PAINT A | MO51N-D-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 1.8
Batch 20/21 | 771-VAMO-4419 | OUT OF SCOPE |  | 771-LPPG-2214 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 600 SS MANU STD T-BAR HANDLE MO51N-D PAINT A | MO51N-D-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 1.8
Batch 21 | 771-VAMO-4420 | OUT OF SCOPE |  | 771-LPPG-2014 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 150 SS MANU STD T-BAR HANDLE MO51N-A PAINT B | MO51N-A-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 21 | 771-VAMO-4421 | OUT OF SCOPE |  | 771-LPPG-2014 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 150 SS MANU STD T-BAR HANDLE MO51N-A PAINT B | MO51N-A-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 21 | 771-VAMO-4422 | OUT OF SCOPE |  | 771-LPPG-2014 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 150 SS MANU STD T-BAR HANDLE MO51N-A PAINT B | MO51N-A-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
| 771-VAMO-4423 | OUT OF SCOPE |  | 771-LPPG-2014 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 150 SS MANU STD T-BAR HANDLE MO51N-A PAINT B | MO51N-A-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 20/21 | 771-VAMO-4424 | OUT OF SCOPE | MoC-TS-155 | 771-LPPG-2020 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 300 SS MANU STD T-BAR HANDLE MO51N-B PAINT B | MO51N-B-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 21 | 771-VAMO-4425 | OUT OF SCOPE |  | 771-LPPG-2020 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 300 SS MANU STD T-BAR HANDLE MO51N-B PAINT B | MO51N-B-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 20/21 | 771-VAMO-4426 | OUT OF SCOPE | MoC-TS-155 | 771-LPPG-2020 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 300 SS MANU STD T-BAR HANDLE MO51N-B PAINT B | MO51N-B-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 20/21 | 771-VAMO-4427 | OUT OF SCOPE | MoC-TS-155 | 771-LPPG-2020 | 0.5 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RF x NPTF CL 300 SS MANU STD T-BAR HANDLE MO51N-B PAINT B | MO51N-B-0.5-B | STAINLESS STEEL | 0 | BLK.VLV.MBB.SST | TS Mechanical Package | SO17033 | 4
Batch 18 | 775-VABL-3594 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2046 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VABL-3595 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2047 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VABL-3636 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2138 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VABL-3637 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2142 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18/23 | 775-VABL-3736 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2478 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VABL-3737 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2439 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VABL-3794 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2466 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VABL-3795 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2467 | 0.75 | VALVE BALL FLOATING FB CL 600 RF SS ASME B16.10 LG LEVER BL52N-D PAINT A | BL52N-D-0.75-A | STAINLESS STEEL | 0 | BLK.VLV.BAL.SST | TS Mechanical Package | SO17033 | 16
Batch 18 | 775-VADB-3524 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2143 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18 | 775-VADB-3525 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2144 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18 | 775-VADB-3526 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2139 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18 | 775-VADB-3527 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2141 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18 | 775-VADB-3529 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2140 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18/27 | 775-VADB-3542 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2048 | 0.75 | VALVE DOUBLE BLOCK & BLEED RB RTJ CL 2500 LTCS MANU STD LEVER DB12N-B PAINT A | DB12N-G-0.75-A | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 55
Batch 18/27 | 775-VADB-3543 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2049 | 0.75 | VALVE DOUBLE BLOCK & BLEED RB RTJ CL 2500 LTCS MANU STD LEVER DB12N-B PAINT A | DB12N-G-0.75-A | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 55
Batch 18/27 | 775-VADB-3547 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2227 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 15000 HIGH YIELD CS MANU STD GEARBOX DB97N-L PAINT A | DB97N-L-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.DBB.HST | TS Mechanical Package | SO17033 | 900
Batch 18/27 | 775-VADB-3548 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2228 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 15000 HIGH YIELD CS MANU STD GEARBOX DB97N-L PAINT A | DB97N-L-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.DBB.HST | TS Mechanical Package | SO17033 | 900
Batch 18 | 775-VADB-3724 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2442 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18 | 775-VADB-3725 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2445 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 19 | 775-VADB-3726 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2444 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package - Was tag 775-VADB-3126 | SO17033 | 250
Batch 18 | 775-VADB-3727 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2441 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18 | 775-VADB-3729 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2440 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 10000 DSS MANU STD GEARBOX DB27N-K PAINT A | DB27N-K-1.81-A | DUPLEX STAINLESS STEEL | 0 | BLK.VLV.DBB.DSS | TS Mechanical Package | SO17033 | 250
Batch 18/27 | 775-VADB-3742 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2449 | 0.75 | VALVE DOUBLE BLOCK & BLEED RB RTJ CL 2500 LTCS MANU STD LEVER DB12N-B PAINT A | DB12N-G-0.75-A | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 55
Batch 18/27 | 775-VADB-3743 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2448 | 0.75 | VALVE DOUBLE BLOCK & BLEED RB RTJ CL 2500 LTCS MANU STD LEVER DB12N-B PAINT A | DB12N-G-0.75-A | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 55
Batch 18/27 | 775-VADB-3747 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2462 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 15000 HIGH YIELD CS MANU STD GEARBOX DB97N-L PAINT A | DB97N-L-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.DBB.HST | TS Mechanical Package | SO17033 | 900
Batch 18/27 | 775-VADB-3748 | OUT OF SCOPE | MoC-TS-087 | 775-LPPL-2463 | 1.81 | VALVE DOUBLE BLOCK & BLEED FB RTJ CL 15000 HIGH YIELD CS MANU STD GEARBOX DB97N-L PAINT A | DB97N-L-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.DBB.HST | TS Mechanical Package | SO17033 | 900
Batch 18 | 775-VAMO-3903 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2044 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3904 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2044 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3905 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2044 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3906 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2044 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3911 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2055 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3912 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2055 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3913 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2055 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 775-VAMO-3914 | OUT OF SCOPE | MoC-TS-087 | 775-LPPG-2055 | 1.81 | VALVE DOUBLE BLOCK & BLEED MONOFLANGE RTJ x CONE & THRD CL 10000 HIGH YIELD CS MANU STD T-BAR HANDLE MO81N-K PAINT A | MO81N-K-1.81-A | HIGH YIELD CARBON STEEL | 0 | BLK.VLV.MBB.HST | TS Mechanical Package | SO17033 | 12
Batch 18 | 777-VADB-3500 | OUT OF SCOPE | MoC-TS-054 | 777-LPFG-2007 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RTJ x NPTF CL 300 LTCS MANU STD LEVER DB04N-B PAINT D | DB04N-B-0.5-D | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 4
Batch 18 | 777-VADB-3501 | OUT OF SCOPE | MoC-TS-054 | 777-LPFG-2007 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RTJ x NPTF CL 300 LTCS MANU STD LEVER DB04N-B PAINT D | DB04N-B-0.5-D | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 4
Batch 18 | 777-VADB-3502 | OUT OF SCOPE | MoC-TS-054 | 777-LPFG-2007 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RTJ x NPTF CL 300 LTCS MANU STD LEVER DB04N-B PAINT D | DB04N-B-0.5-D | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 4
Batch 18 | 777-VADB-3503 | OUT OF SCOPE | MoC-TS-054 | 777-LPFG-2007 | 0.5 | VALVE DOUBLE BLOCK & BLEED RB RTJ x NPTF CL 300 LTCS MANU STD LEVER DB04N-B PAINT D | DB04N-B-0.5-D | LOW TEMPERATURE CARBON STEEL | 0 | BLK.VLV.DBB.LST | TS Mechanical Package | SO17033 | 4